# NCR ServiceDesk Integration

Snowfall Proactive Alerts - Jira Epic and Subtasks

Project: UK Snowfall Data Pipeline

Date: April 2026

Ref Doc: NCR Service Desk Web Services Technical Doc v3.2

Eng Doc: docs/ncr-integration-auth-setup.md

# EPIC: NCR ServiceDesk Integration - Snowfall Proactive Alerts

Issue Type: Epic

Priority: Medium

Labels: ncr, integration, proactive-alerts, snowfall

Integrate the McDonald's UK Snowfall proactive alerts Lambda with the NCR Service Desk SOAP API so that device incidents detected by Snowfall automatically raise tickets in the NCR system. When a proactive alert fires the system calls NCR's createServiceRequest SOAP operation and stores the NCR ticket ID back in DynamoDB when NCR confirms via an async outbound callback.

Architecture: AWS Lambda -> NCR SOAP API (mTLS + WS-Security) + NCR callback -> API Gateway -> snowfall-ncr-callback Lambda -> DynamoDB

| Story | Subtasks | Can Start Now? |
| --- | --- | --- |
| 1 - NCR Onboarding & Credentials | 6 | Yes - raise request today |
| 2 - SSL Certificate Procurement | 8 | Partially - buy cert now, CN needs Story 1.5 |
| 3 - AWS Infrastructure | 6 | Yes - no NCR dependency |
| 4 - Lambda Engineering | 5 | Yes - mock NCR responses |
| 5 - CERT Environment Testing | 6 | Blocked on Stories 1 and 2 |
| 6 - PROD Go-Live | 3 | Blocked on Story 5 |
| TOTAL | 34 |  |

## STORY 1 - NCR Onboarding and Credential Provisioning

Priority: Highest

Can Start: Yes - immediately

Blocked by: Nothing

All engineering is blocked on NCR provisioning credentials and confirming field mappings. This story tracks all onboarding items. Reference: docs/ncr-integration-auth-setup.md (questions 1-19).

| # | Subtask | Priority | Blocked by |
| --- | --- | --- | --- |
| 1.1 | Raise NCR integration onboarding request | Highest | - |
| 1.2 | Schedule NCR onboarding call | Highest | 1.1 |
| 1.3 | Obtain CERT endpoint URL and SOUP credentials from NCR | High | 1.2 |
| 1.4 | Obtain PROD endpoint URL and SOUP credentials from NCR | High | 1.2 |
| 1.5 | Confirm NCRMCN, SourceSystem, SiteShortName, AssetID with NCR | High | 1.2 |
| 1.6 | Confirm NCR outbound callback authentication method | High | 1.2 |

Subtask 1.1: Raise NCR Integration Onboarding Request

Contact the NCR integration/onboarding team to formally request a new customer integration. Reference the NCR Service Desk Web Services Technical Doc v3.2. Date-stamp the request to protect the project timeline if NCR is slow to respond.

Subtask 1.2: Schedule NCR Onboarding Call

Book the onboarding call with the NCR integration team. Share docs/ncr-integration-auth-setup.md with 19 open questions ahead of the call so NCR can prepare answers.

Subtask 1.3: Obtain CERT Environment SOAP Endpoint URL and SOUP Credentials

NCR to provide: CERT endpoint URL, CERT SOAP USERID, CERT SOAP Password (min 24 chars). Store in AWS Secrets Manager under ncr/credentials-cert.

Subtask 1.4: Obtain PROD Environment SOAP Endpoint URL and SOUP Credentials

NCR to provide: PROD endpoint URL, PROD SOAP USERID, PROD SOAP Password. Must be separate from CERT credentials per NCR spec.

Subtask 1.5: Confirm Customer Field Mappings with NCR

Confirm: NCRMCN value for McDonald's UK, SourceSystem identifier, restaurant number format to SiteShortName mapping, device ID format to AssetID mapping, SSDGCustomer value, CallType to use (HELPDESK or MAIN).

Subtask 1.6: Confirm NCR Outbound Callback Authentication Method

Ask NCR how they authenticate when calling our callback endpoint. Options: Basic auth, API key, IP whitelist, or client certificate. Required before we can secure the API Gateway endpoint.

## STORY 2 - SSL Client Certificate Procurement and Registration

Priority: High

Can Start: Partially - buy cert now; CN format needs Story 1.5

Blocked by: 1.5 for CSR generation

NCR requires mTLS: a commercial client certificate from DigiCert, GoDaddy, Thawte, Comodo, or GeoTrust. We generate the cert and register the public certificate with NCR. Private key stays in AWS Secrets Manager. Separate certs required for CERT and PROD.

| # | Subtask | Priority | Blocked by |
| --- | --- | --- | --- |
| 2.1 | Purchase commercial SSL certificate - CERT env | High | - |
| 2.2 | Generate CSR and private key - CERT env | High | 1.5 |
| 2.3 | Submit CSR to CA, receive signed certificate - CERT | High | 2.2 |
| 2.4 | Register client certificate with NCR - CERT env | High | 2.3 |
| 2.5 | Purchase commercial SSL certificate - PROD env | Medium | - |
| 2.6 | Generate CSR and private key - PROD env | Medium | 1.5 |
| 2.7 | Submit CSR to CA, receive signed certificate - PROD | Medium | 2.6 |
| 2.8 | Register client certificate with NCR - PROD env | Medium | 2.7 |

Subtask 2.1: Purchase Commercial SSL Certificate - CERT Environment

Purchase from one of the 5 NCR-approved CAs: DigiCert, GoDaddy, Thawte, Comodo, or GeoTrust. Standard SSL/TLS certificate for client authentication. Self-signed certificates will not be accepted by NCR.

Subtask 2.2: Generate CSR and Private Key - CERT Environment

Generate using openssl: openssl req -new -newkey rsa:2048 -nodes -keyout mcdonalds-uk-ncr-cert.key -out mcdonalds-uk-ncr-cert.csr -subj "/CN=<confirm-with-NCR>/O=McDonalds UK Ltd/C=GB". CN name format must be confirmed with NCR (Subtask 1.5) before generating.

Subtask 2.3: Submit CSR to CA and Receive Signed Certificate - CERT

Submit the CSR to the chosen commercial CA. Store the returned signed .crt PEM safely. Expected turnaround: 1-5 business days.

Subtask 2.4: Register Client Certificate with NCR - CERT Environment

Send the signed public certificate (.crt only, never the private key) to the NCR integration team for registration in their system. Confirm registration is complete before running any tests.

Subtask 2.5-2.8: PROD Environment Certificates

Repeat subtasks 2.1-2.4 for the PROD environment. NCR spec explicitly states separate certificates are required for CERT and PROD (do not reuse the CERT certificate).

## STORY 3 - AWS Infrastructure

Priority: High

Can Start: Yes - no NCR dependency

Blocked by: Nothing

All AWS infrastructure can be built now. Includes Secrets Manager secrets with placeholder values, IAM policy updates, the new snowfall-ncr-callback Lambda, API Gateway REST endpoint, and DynamoDB schema additions. All managed via Terraform.

| # | Subtask | Priority | Blocked by |
| --- | --- | --- | --- |
| 3.1 | Create Secrets Manager secrets for NCR credentials | High | - |
| 3.2 | Update IAM role for proactive-alerts Lambda | High | - |
| 3.3 | Add ncr_* fields to proactive_alerts_table DynamoDB | High | - |
| 3.4 | Build snowfall-ncr-callback Lambda | High | - |
| 3.5 | Build API Gateway REST POST endpoint for NCR callback | High | 3.4 |
| 3.6 | Write Terraform for callback Lambda and API Gateway | High | 3.4 |

Secrets Manager secrets to create:

ncr/credentials       ->  { userid: TBC, password: TBC }

ncr/client-cert-cert  ->  PEM certificate (CERT env)

ncr/client-key-cert   ->  PEM private key (CERT env)

ncr/client-cert-prod  ->  PEM certificate (PROD env)

ncr/client-key-prod   ->  PEM private key (PROD env)

New DynamoDB attributes on proactive_alerts_table:

ncr_transaction_id  - our GUID (set on createServiceRequest call)

ncr_create_status   - SUCCESS / FAILED / SKIPPED

ncr_ticket_id       - INCxxxxxxx (set by callback Lambda when NCR calls back)

ncr_ticket_status   - PENDING_NCR_ID / OPEN / ASSIGNED / COMPLETED etc

## STORY 4 - Lambda Engineering: NCR Integration Code

Priority: High

Can Start: Yes - build with mocked NCR responses

Blocked by: Nothing (swap real endpoint when creds arrive)

Implement create_ncr_ticket() in the existing snowfall-proactive-alerts Lambda and wire into process_rule(). NCR call failure must not block email sending. Build and unit-test against mocked SOAP responses before real CERT credentials are available.

| # | Subtask | Priority | Blocked by |
| --- | --- | --- | --- |
| 4.1 | Add mTLS cert loading from Secrets Manager into /tmp | High | - |
| 4.2 | Write create_ncr_ticket() - SOAP call and ACK parse | High | 4.1 |
| 4.3 | Add XML character escaping for all SOAP user-generated fields | High | - |
| 4.4 | Wire create_ncr_ticket() into process_rule() flow | High | 4.2, 3.3 |
| 4.5 | Add NCR_ENV / NCR_ENDPOINT / NCR_NCRMCN env vars to Terraform | Medium | - |

Acceptance criteria:

SOAP XML built with correct WS-Security header and all required NCR fields

mTLS cert loaded at cold start, reused on warm Lambda invocations

ncr_transaction_id and ncr_create_status stored in DynamoDB on every alert

NCR call failure logs error but does not fail the Lambda or block email sending

XML special characters escaped in all user-generated fields: &, <, >, ", '

TransactionID is deterministic per alert_id (idempotent re-submission safe)

## STORY 5 - CERT Environment Testing

Priority: High

Can Start: No

Blocked by: Stories 1, 2, 3, 4 complete

Full end-to-end testing against NCR CERT (test) environment before any PROD activity.

| # | Subtask | Priority | Blocked by |
| --- | --- | --- | --- |
| 5.1 | Provide NCR with our callback endpoint URL for registration | High | 3.5 |
| 5.2 | CERT test: Lambda creates ticket in NCR successfully | High | 1.3, 2.4 |
| 5.3 | CERT test: NCR callback delivers NCRTicketID to DynamoDB | High | 5.2 |
| 5.4 | CERT test: cooldown prevents duplicate tickets | High | 5.2 |
| 5.5 | CERT test: one ticket created per restaurant (not bulk) | Medium | 5.2 |
| 5.6 | Obtain CERT environment sign-off from NCR | High | 5.2-5.5 |

## STORY 6 - PROD Go-Live

Priority: Medium

Can Start: No

Blocked by: Story 5 sign-off

| # | Subtask | Priority | Blocked by |
| --- | --- | --- | --- |
| 6.1 | Populate PROD credentials and certificates in Secrets Manager | Medium | 1.4, 2.8 |
| 6.2 | PROD smoke test: end-to-end ticket creation and callback | Medium | 6.1 |
| 6.3 | PROD go-live sign-off and CloudWatch alarm on NCR failures | Medium | 6.2 |

## Indicative Timeline

| Period | Activity |
| --- | --- |
| Week 1-2 | Raise NCR onboarding request, schedule call, start cert purchase |
| Week 3-4 | CERT credentials and endpoint received from NCR. Engineering complete (mocked). |
| Week 5-6 | CERT client cert registered with NCR. Swap mock with real endpoint. CERT testing begins. |
| Week 7-8 | CERT testing back-and-forth, sign-off obtained. |
| Week 9-10 | PROD cert and credential steps. |
| Week 11-12 | PROD testing, go-live. |
| Optimistic | 6-8 weeks |
| Realistic | 10-12 weeks |
| NCR slow | 4-6 months (common with NCR onboarding) |

NOTE: Engineering (Stories 3 and 4) can be completed within 2-3 weeks and will be ready and waiting. The critical path is entirely driven by the NCR onboarding and certificate registration process. Raise the onboarding request (Subtask 1.1) today to start the clock.